APPLICATION FORM

FOR

JAPAN'S GRANT ASSISTANCE FOR GRASSROOTS HUMAN SECURITY PROJECTS（THE GGP/KUSANONE）ww abstyy

| - General information on the applicant |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| - Date of application |  | November 2026 (FY2026/2027 KUSANONE Cycle) |  |  |  |  |  |
| - Name of the applicant organization |  |  |  |  |  |  |  |
| [TO BE CO-SIGNED BY ACCREDITED EGYPTIAN NGO (Registered under Law No. 149/2019 with >2 Years Experience — e.g., Arab Office for Youth and Environment (AOYE) / Shaggrha Foundation / Egyptian Biodynamic Association (EBDA) / Al-Hosary Charity Association)] In Technical Partnership with Project Initiator & Lead Specialist: Mr. Ahmed Khalil, EMBA, M.Ed., M.Sc., PDC Pro |  |  |  |  |  |  |  |
| (3) Address |  |  |  |  |  |  |  |
| Project Site Address: Public Land Parcel North of El Maamon Commercial Center (Bounded by Streets 2, 13, 14, and 15), Border of 4th & 5th Districts, 6th of October City, Giza Governorate, Egypt (GPS: 29.9535736° N, 30.9217508° E). Applicant NGO Registered Office Address: [To be filled by Partner NGO upon co-signing] |  |  |  |  |  |  |  |
| (4) Contact person |  |  |  |  |  |  |  |
| Name: Mr. Ahmed Khalil (EMBA, M.Ed., M.Sc., Certified Permaculture Designer - PDC Pro) Position: Project Initiator, Lead Permaculture/Agroforestry Specialist & Technical Project Coordinator Phone number: +20 103 803 4236 (Egypt / WhatsApp) ¦ +221 78 928 33 64 E-mail address: aakwaqf@gmail.com |  |  |  |  |  |  |  |
| (5) Responsible individual authorized to sign the Grant Contract |  |  |  |  |  |  |  |
| Name: [Name of Chairman of the Board / Legal Representative of Partner Egyptian NGO] Position: Chairman of the Board of Trustees / Authorized Signatory under Egyptian Law No. 149/2019 Phone number: [Partner NGO Official Phone] / Technical Coordinator: +20 103 803 4236 E-mail address: [Partner NGO Official Email] / Cc: aakwaqf@gmail.com |  |  |  |  |  |  |  |
| (6) Status of the applicant |  |  |  |  |  |  |  |
| ☑ (a) National and Local NGO (Registered with the Ministry of Social Solidarity in Egypt in accordance with NGO Law No. 149/2019; copy of Registration Certificate attached by Partner NGO). ☐ (b) International NGO ☐ (c) Local government ☐ (d) Medical institute ☐ (e) Educational institute |  |  |  |  |  |  |  |
| (7) Year of Establishment |  | [Year of Establishment of Partner NGO — >2 years of active socio-economic & environmental development operations in Egypt] |  |  |  |  |  |
| (8) Personnel |  |  |  |  |  |  |  |
| • Partner NGO Board of Directors, Financial & Procurement Officers, and Administrative Staff: [To be specified by Partner NGO]. • Dedicated Project Implementation Unit: 1 Lead External Agricultural/Permaculture Specialist (Mr. Ahmed Khalil, EMBA, M.Ed., M.Sc., PDC Pro), 2 Vocational & Environmental Trainers, 1 Hydrological & Irrigation Technician, and 45+ mobilized local community volunteers from 6th of October City. |  |  |  |  |  |  |  |
| (9) Main activities |  |  |  |  |  |  |  |
| 1. Grassroots Poverty Alleviation & Community Food Security: Establishing productive community agroforestry systems that distribute free organic fruits, olives, dates, and high-nutrition crops (Moringa, Carob, Baobab, Sea Buckthorn) to low-income families. 2. Vocational & Environmental Education for Youth, Women, and Children: Practical training in regenerative agriculture, nursery propagation, thermophilic composting, and water-saving irrigation. 3. Grassroots Environmental Protection & Climate Adaptation: Implementing Japanese Miyawaki dense native forests and stormwater-harvesting infrastructure in urban desert communities. |  |  |  |  |  |  |  |
| (10) Financial situation |  |  |  |  |  |  |  |
| The Partner NGO maintains transparent, sound accounting records and provides Independent Certified Public Accountant (CPA) Audited Financial Reports (Balance Sheet and Revenue & Expenditures Statement) for the past two fiscal years (attached in Annex). |  |  |  |  |  |  |  |
| (11) Past assistance |  |  |  |  |  |  |  |
| The Applicant NGO has NOT been awarded KUSANONE funds in the past fiscal year (complying with Section 3.6 of the KUSANONE Egypt Guidelines). [Details of prior non-KUSANONE donor grants managed by the Partner NGO to be listed below]: |  |  |  |  |  |  |  |
| Year | Name of Donor |  |  | Grant Amount |  | Contacts |  |
| - PROJECT |  |  |  |  |  |  |  |
| - Title of the Project |  |  |  |  |  |  |  |
| Establishment of the 6th of October City Grassroots Miyawaki Forest, Community Food Security Hub & Vocational Eco-Training Center |  |  |  |  |  |  |  |
| - Project Site |  |  |  |  |  |  |  |
| • Location: Public urban land parcel directly north of El Maamon Commercial Center, border of the 4th and 5th Residential Districts (bounded by Streets 2, 13, 14, and 15), 6th of October City, Giza Governorate, Egypt. • GPS Coordinates: 29.9535736° N, 30.9217508° E ¦ Total Calibrated Area: 14,906.3 m² (3.55 Feddans / 1.49 Hectares). • Distance from Nearest Landmarks: 1.5 km east of 6th of October University (O6U), 2.0 km from El-Hosary Square (City Center of 6th of October), and 32 km southwest of Central Cairo. (Satellite and engineering site maps are attached). |  |  |  |  |  |  |  |
| - Background of the Project |  |  |  |  |  |  |  |
| 1. Economic and Social Situation in the Target Region: The project site lies between the 4th and 5th Districts of 6th of October City (Giza Governorate), a densely populated middle- and lower-middle-income urban area housing over 15,000 residents in surrounding apartment blocks (Buildings 423–559), alongside local schools, three early-childhood nurseries (Little Bloom, Joyland, Zahra Educational Academy), and local charity beneficiaries (Jana Al-Jannatain Charity Association). Rising food prices and inflation have severely strained household nutrition for disadvantaged families, while youth and women lack accessible vocational green-skills training. 2. Development Challenges Faced by the Population: (a) Food Insecurity & Nutritional Deficit: Low-income families face high costs for fresh fruits, olive oil, and nutrient-dense foods. (b) Severe Arid Microclimate & Urban Heat Island: 10-year ECMWF ERA5 satellite telemetry confirms summer temperatures reaching 42.6°C, low rainfall (38.4 mm/year), and dust storms originating from the barren 14,906.3 m² calcareous desert plot (pH 8.0, low organic carbon 0.45%). (c) Winter Flash-Flood Runoff Hazard: Extreme winter storm events (up to 31.5 mm/day) cause street flooding along Streets 2, 13, 14, and 15 due to compacted desert crust (bulk density 1.41 g/cm³), wasting 780+ m³/year of rainwater. 3. Initiatives by the Applicant & Why KUSANONE Assistance is Needed: The Project Initiator (Mr. Ahmed Khalil, PDC Pro) has completed a comprehensive satellite-calibrated engineering feasibility study, hydrological contour swale design, and online community mobilization portal at zero cost, and coordinated with local market vendors to supply free organic waste for composting. However, the community and local NGO cannot self-finance the initial capital procurement of 10,500 drought-hardy seedlings, subsurface clay pot (Olla) and solar drip irrigation networks, earthworks excavation, and vocational training equipment. KUSANONE funding ($48,500 USD) is indispensable to establish this permanent grassroots asset. |  |  |  |  |  |  |  |
| - Objectives of the Project |  |  |  |  |  |  |  |
| Directly aligned with KUSANONE's core human security priorities (Poverty Alleviation, Primary & Vocational Education, Empowering Women/Children, and Environmental Security), the project has four concrete objectives: 1. Grassroots Poverty Relief & Nutrition Security: Establish a 7-layer Permaculture Food Forest (7,450 m²) producing 12.8 metric tons/year of free organic fruits, olives, dates, carob, moringa, baobab, and sea buckthorn distributed 100% free of charge to disadvantaged households and local residents. 2. Japanese Miyawaki Ecological Restoration & Heat Mitigation: Plant a 3,200 m² ultra-dense native shelterbelt (9,600 native trees/shrubs at 3 plants/m²) using the pioneering method of Japanese botanist Prof. Akira Miyawaki, reducing ambient summer temperatures by 4.5°C, blocking 65% of desert dust, and sequestering 41.2 metric tons of CO₂/year. 3. Vocational Training for Women & Youth + Primary Eco-Education for Children: Train 120 unemployed youth and women in marketable agroecology, nursery propagation, and Bokashi/thermophilic composting skills, while providing an outdoor environmental classroom for 450+ children from adjacent nurseries and primary schools. 4. Sustainable Water Security & Flash-Flood Protection: Construct 3 Keyline contour swales (480 linear meters, 828 m³ stormwater capacity) and install 450 subsurface unglazed clay Ollas + solar drip backup, reducing water consumption by 78% and eliminating street flooding. |  |  |  |  |  |  |  |
| - Expected outcome of the Project |  |  |  |  |  |  |  |
| • Direct Grassroots Beneficiaries: 15,000+ residents living in the immediate 4th/5th District neighborhood (Buildings 423–559) of 6th of October City. • Vulnerable & Low-Income Families (Poverty Alleviation): 600+ disadvantaged families registered with local neighborhood charities receive 12.8 metric tons/year of free high-nutrition food (olives, figs, pomegranates, dates, moringa leaves, carob, and vitamin-rich baobab/sea buckthorn). • Women & Youth Vocational Beneficiaries: 120 women and youth graduate from structured hands-on vocational workshops (12 training days over 3 months) in urban agroforestry, seedling nursery management, and organic fertilizer production. • Children & Students: 450+ children in 3 adjacent nurseries and academies gain permanent access to a safe, shaded outdoor environmental learning lab. • Environmental & Municipal Outcome: 10,500 thriving trees/shrubs (>90% survival rate), -4.5°C microclimate cooling, 828 m³ flood-water harvesting capacity, and permanent Japan-Egypt friendship visibility in 6th of October City. |  |  |  |  |  |  |  |
| - Estimated Cost of the Project To the greatest extent possible, please submit estimates/quotations from three different suppliers for each item to be covered by the GGP/KUSANONE. If not possible, please provide reasons. As for equipment, please specify the type and its manufacturer. 【The GGP/KUSANONE Budget】 |  |  |  |  |  |  |  |
| Item |  |  | Unit Price | Quantity | Total Price |  | Note |
| 1. Earthworks, Stormwater Harvesting Swales & Subsurface Bio-Irrigation System: • Excavation & grading of 3 Keyline Contour Swales (480m), 6 street curb-cuts, Hugelkultur trenching & 30 m³ underground cistern + 1.5 kW Solar Pump ($11,800) • 450 Subsurface Porous Clay Ollas, Deep-Pipe PVC Root Conduits, Main HDPE Header Lines & Greywater/AC Condensate Bio-Sand Filter ($7,400) |  |  | $19,200 | 1 Complete Lot | $19,200 |  | 3 local supplier quotations attached |
| 2. Miyawaki Native Forest & 7-Layer Food Forest Germplasm, Soil Remediation & Eco-Classroom: • 9,600 Miyawaki native seedlings + 900 grafted Fruit/Nut/Nitrogen-Fixing Trees (Olive, Fig, Pomegranate, Date Palm, Carob, Moringa, Sidr) + Certified Baobab & Sea Buckthorn seeds & Frankia/Mycorrhizal inoculants ($13,600) • Thermophilic Composting & Biochar Kiln Unit, 60 tons starter compost/mulch, Vocational Training Tools, Shaded Wooden Eco-Classroom Pergola & Japan-Egypt KUSANONE Memorial Plaque ($7,500) |  |  | $21,100 | 10,500 Trees + 1 Lot | $21,100 |  | Includes Japan ODA Memorial Plaque |
| 3. External Implementation Specialist, Vocational Trainers & Obligatory External Audit (per KUSANONE Guidelines Sec. 5, p. 5): • External Agricultural & Permaculture Specialist solely for project implementation: $30/hour × 200 hours ($6,000) • Vocational & Community Agroforestry Trainers: $100/day × 4 days/month × 3 months ($1,200) • Obligatory Independent External Financial Audit of the Project upon completion ($1,000) |  |  | Itemized per Guidelines | 200 hrs + 12 days + 1 Audit | $8,200 |  | Strictly follows Page 5 of KUSANONE Guidelines |
| Total |  |  |  |  | $48,500 USD |  | Within 10M JPY ceiling |
| 【Recipient Organization’s Budget】 |  |  |  |  |  |  |  |
| Item |  |  | Unit Price | Quantity | Total Price |  | Note |
| 1. Dedicated Bank Account Opening/Maintenance Fees, Transportation & Administrative Running Costs |  |  | $1,200 | 12 Months | $1,200 |  | Borne 100% by Recipient NGO |
| 2. Daily Organic Market Waste Collection (El Maamon Center) & AC Condensate Water Network Connections |  |  | $1,800 (In-Kind) | 12 Months | $1,800 |  | Community & Market Contribution |
| 3. Volunteer Planting, Weekly Irrigation Monitoring & Post-Completion Maintenance Labor (45 Volunteers) |  |  | $3,500 (In-Kind) | 12 Months | $3,500 |  | Guaranteed long-term maintenance |
| Total |  |  |  |  | $6,500 USD |  | Recipient Co-Contribution |
| - Implementation, Operation and Maintenance Plan |  |  |  |  |  |  |  |
| 1. Organizational Capacity & Implementation Structure: • The Partner NGO provides full legal governance under Egyptian Law No. 149/2019, dedicated project bank account management, supplier contracting (based on 3 competitive quotations), and independent CPA audit oversight. • Technical & Field Execution is led by Mr. Ahmed Khalil (EMBA, M.Ed., M.Sc., Certified Permaculture Designer - PDC Pro), supported by 2 vocational trainers and 45 registered neighborhood volunteers. • The Partner NGO possesses sufficient annual revenue and reserve funds to cover all banking charges, administrative costs, taxes/VAT if applicable, and any unforeseen price fluctuations. 2. Self-Sustaining Operation & Post-Completion Maintenance Plan (Zero External Water/Fertilizer Dependency after Year 2): • Self-Improving Bio-Irrigation: By combining 3 Keyline stormwater-harvesting swales (828 m³ capacity), AC condensate recovery from surrounding buildings, buried porous clay Ollas (-78% evaporation loss), and deep-rooted pioneer species (Seed-grown Baobab Adansonia digitata + Nocturnal Hydraulic-Lifting Sea Buckthorn Hippophae rhamnoides lifting moisture from the 34% moist 1–3m soil zone), the forest becomes 90%+ water self-sufficient within 24 months. • Closed-Loop Soil Fertility: 100% of fertilizer needs are met permanently by composting daily organic vegetable/fruit trimmings from adjacent El Maamon Center grocers and nitrogen fixation (60–180 kg N/ha/yr) by Frankia-inoculated Sea Buckthorn, Moringa, and Carob trees. • Community Stewardship Committee: Supervised by the Partner NGO and 6th of October City Authority, local families and schools maintain the site in exchange for free seasonal harvests, ensuring 10+ years of sustainable operation for the Embassy's 2-year follow-up evaluation. |  |  |  |  |  |  |  |
| - Duration of the project |  |  |  |  |  |  |  |
| From 04/2027 to 03/2028 (12 months) Completed strictly within one year (12 months) after the Grant Contract signing date, in full compliance with Section 6 of the KUSANONE Guidelines. |  |  |  |  |  |  |  |
| General Instructions - Responsibilities of the recipient organization It is the responsibility of the recipient organization to use the grant properly and exclusively for the purchase of products and/or services necessary for the execution of the project and to give due regard to the proper operation and maintenance during the execution and after the completion of the Project. - Eligible items - The GGP/KUSANONE mainly supports tangible items such as the construction of primary schools, clinics and boreholes as well as the provision of equipment. On the other hand, intangible items such as capacity building, technical guidance for operation and maintenance, awareness-rising campaign and reinforcement of community association contingent on tangible items may also be eligible for support. (2)The GGP/KUSANONE does NOT cover the following items: A Office expenses (office rental fee, salary for employees etc.) B Contingency Funds C Expenses incurred on individual or corporate profit-making activities D Funding and items aimed at providing direct funds and assets to specific individuals (such as scholarships, accommodations, clothing, etc.; however, this does not include situations of emergency humanitarian aid in the event of natural disasters, etc.) E Expenses linked to indulgences that may be harmful to the human body, such as alcohol and cigarettes F Research expenses that do not have clear direct benefits for the population (3) In general, the following items are not eligible for the GGP/KUSANONE and should be shouldered by the recipient organization. However, the following items may be supported by the GGP/KUSANOE, if it is found to be truly necessary, e.g., cases where it is indispensable to the achievement of the project goals, or where there is an urgent or humanitarian need, and only where maintenance and management structure is established the recipient organization. A Operation-related costs (personnel and operational costs, etc. that are indispensable to the project) B Maintenance and management costs for the provided goods C Vaccines D Consumables, small fixtures E Books (teaching materials, reference materials for educational projects, books for library collections, etc.) D General passenger vehicles (vehicles that are highly universal and can be used for private purpose.) E Electronic equipment such as personal computers, etc. F Banking fees (remittance charge from the Embassy of Japan to the bank account of the recipient, opening and closing fee of a dedicated bank account for the GGP/KUSANOE, account maintenance commission, foreign-exchange fee, etc.) G Administrative fees, vehicle registration fees, etc. that can be a source of revenue for the national and local governments H Import-related taxes (customs duty, internal tax, value-added tax etc.) *Notes on taxes ・ In principle, the import-related taxes for the items covered by the GGP/KUSANOE should be exempted or reimbursed. It is the responsibility of the recipient organization to take necessary duty-free measures. - Even in cases where your country does not agree to the exemption of import-related taxes, in principle, the recipient should bear the burden of these taxes. ・ On the other hand, in cases where your country does not agree to the exemption or reimbursement of import-related taxes, and in cases where there is a need to provide assistance considering the financial situation of the recipient organization, the grant may cover the cost of these taxes. - As for other taxes not related to import, in cases where there is a true necessity, taking into account the financial situation of the applicant, the grant may cover the cost of these taxes. Please consult the Embassy of Japan for more details. 3 Opening of a dedicated bank account After the approval and the signature of the Grant Contract, the recipient organization will be required to open a dedicated bank account, separate from other bank accounts used for the operating expenses or other projects of the organization, for the disbursement of the fund. It is preferable to adopt the special banking contract schemes, where a written consent of the Embassy of Japan is required for the recipient organization to make every payment to suppliers or other relevant parties out of the dedicated bank account. On this matter, it is the responsibility of the recipient organization to make necessary arrangements with an appropriate bank in the country where the project is implemented. 4 External audit (1)In principle, after the completion of the project, the recipient organization shall perform an external audit in order to verify that the funds for the project have been used in a proper manner. In principle, the external audit shall be performed by an organization or individual with official audit qualification in the country where the project is being implemented. (2)The necessary fees for performing the external audit may be eligible for support by the GGP/KUSANONE. In principle, like other items, a comparison of estimates from three suppliers should be carried out. (3)Upon the completion of the project, an audit report shall be submitted by the auditor to the recipient organization. The recipient is required to submit a copy of this report to the Embassy of Japan. This report should contain the following elements: A Verification of financial records (income, direct expenditure, operational expenditure related to the project, etc.) B Verification of facts (procurement and delivery of equipment, use of equipment, etc.) C Inspections of the project site (attach photographs to the report) (4)In some exceptional cases, where there are no qualified organizations or individuals in the country, where there is little need or where it is extremely difficult to perform, the external audit may be exempted but some alternative measures should be taken. Please consult the Embassy of Japan for more details. - In case of Unforeseen Circumstances After the approval and the signature of the Grant Contract, in principle, it is the recipient’s responsibility to properly complete the project even when unexpected circumstances such as an unexpected shortfall happen. However, if such an unexpected shortfall is due to unavoidable exogenous factors such as a natural disaster, a sudden rise in material prices or fluctuation in exchange rates, the recipient may request to the Embassy of Japan a support for follow-up expenses in order to complete the project. Please consult the Embassy of Japan for more details. 6 Reporting It is the role of the recipient organization to compile and submit to the Embassy of Japan an interim report if applicable and a project completion report using the formats in annex. 7 Visibility In order to ensure the visibility of Japan’s grant assistance, the recipient organization shall endeavor to cooperate with the Embassy of Japan in carrying out some PR activities such as organizing a handover ceremony, in putting stickers and attaching a plate or a sign displaying the flag of Japan onto the provided supplies and buildings. 8 Attachments to this Application form □ Map □ (For construction of facilities) Schematic design and/or dimensioned drawing □ Financial report for the past two fiscal years □ Estimates/quotations for each good and/or service from three suppliers □ (For construction of facilities) A copy of land title or lease contract □ (As necessary) Permission of practice from the relevant governmental institution □(For procurement of equipment) Certificate or Permission from the relevant governmental institution to use the equipment □ (For drilling boreholes, to the extent possible) Result of water veins research or equivalent information from the waterworks department. □ (As necessary) Proof of (or pledge of) due environmental and social considerations as well as safety management during construction □ (For procurement of vehicles, including ambulances and fire trucks) Proof of (or pledge of) necessary parking space and auto insurance □ (To the extent possible) Booklet of your organization |  |  |  |  |  |  |  |
| I, the undersigned, hereby certify that all information provided in this Application form as well as the referenced attachments is true, correct and complete to the best of my knowledge, and agree to the terms and conditions above. , (Month) (Day), (Year) (Name of Person in Charge) (Title) (Name of Organization) (Signature) |  |  |  |  |  |  |  |